## ListOfFeatures
Product Backlog - Pine & Dine
User Stories / List of features
As a site visitor I want to be able to reserve a table through the website.
As a site visitor I want to be able to see the products in the menu and their prices.
As a site visitor I want to be able to order food online.

## sprint1
Sprint Backlog : Sprint 1 Feb 7 - Feb 11
BACKLOG TASK & ID | STORY POINTS (NR) | ASSIGNED TO | STATUS
Tabel Reservation
Reservation Form | 1 | Ron Kosova | DONE
Form Validation | 3 | Ron Kosova | ONGOING
Writing to Database | 2 | Ron Kosova | ONGOING
Menu
Product Info in Database | 1 | Nazanin Fallah | ONGOING
Reading From Database | 2 | Nazanin Fallah | ONGOING
Menu Page | 1 | Nazanin Fallah | DONE
Showing Menu Coherently | 3 | Nazanin Fallah | ONGOING
Online Order
Write to and Read from Database | 2 | Orges Gashi | ONGOING
Order Page | 3 | Orges Gashi | ONGOING
Universal Footer and Header
Convert HTML files to PHP | 1 | Ron Kosova | DONE
Create footer.php and header.php | 1 | Ron Kosova | DONE
Include in new PHP pages | 1 | Ron Kosova | DONE
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
During this week, you should update your exisiting pages that is your pages have universarl header and footer.
Upload this excel file to your project Repo in GitHub and update it regulaly.
You have planned your features and have distributed work among your team members
You have designed your database. Make sure that each member has his/her own table to work with.
You have create a GitHub repo and each member is added as collaborator.
Please make regular commits and get familiar with the development activities by utilizing version control.
Uploaing your files to GitHub repo is not acceptable. It will have negative impact on your grade.
Ask questions during the consultation sessions if you are not sure about how you are proceeding

## sprint2
Sprint Backlog : Sprint 2 (Feb 14 - Feb 18)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
User Story #1
Task : Make a list of categories of products | 2 | Pekka | Ongoing
Task : List products based on categories | 2 | Juha
Task : Search products | 4 | Johanna
Task: Display products | 2 | Markku
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.

## sprint3
Sprint Backlog : Sprint 3 (Feb 21 - Feb 25)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
User Story #1
Task : Make a list of categories of products | 2 | Pekka | Ongoing
Task : List products based on categories | 2 | Juha
Task : Search products | 4 | Johanna
Task: Display products | 2 | Markku
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.
Finalize your work and start to preare for the project review.
Make sure that your repository, shell.hamk.fi servers all have the latest version of your website.